Sinnissippi Quilters, Inc.

Quilt Show Chair  – 2 Year Term

The Chair is responsible for the initial planning, the show itself, and the show wrap-up.  The Chair is a voting member of the Sinnissippi Quilt Guild Board.  After current show wrap up meeting, all info is turned over to the new Chair.  Preparation should begin 18 months before the next show.  The Chair appoints a committee made up of the following:

| Treasurer | Registration | Program |
| --- | --- | --- |
| Publicity | Set-up | Graphics |
| Judging | Vendors | Quilt Racks |
| Bed-turning | Volunteers | Ribbons |
| Boutique | Silent Auction | Door Prizes |

The Chair determines when the committee meets.  There are notebooks containing job descriptions and all necessary information for each committee that should be passed on to succeeding co-chairs.

The following timeline is for the Chair and the Committee:

18 Months Before the Show:

- Set up show theme, date & site.

- Plan posters, bookmarks & brochures.

- Decide on having any challenges, special exhibits, T-shirts, pins, etc.

- Map out publicity.

- Work on entry forms.

- Discuss vendors, booth cost, deposit, and plan information postcard.

- See that arrangements are made, contract signed, etc. with the venue.

12 Months Before the Show:

1.        Have all art work, graphics, wording, etc. completed and send off to printer.

8 Months Before the Show:

- Begin monthly meetings of committee.

- Check over the floor plan.

- Make sure all forms are up to date; entry, challenge, vendors, etc.

- Vendor contracts should be sent out.

- Choose judges.

- Check all parts of the racks to see what needs to be repaired or replaced.

- Confirm publicity items.

- Give monthly updates at each Guild meeting, on the website and in each    	 	newsletter.

- Talk up Silent Auction and Boutique donations.

- Plan the making of the medallions.

Revised 3/22/2024	Page 1 of 2 	Job Description – Quilt Show Chair

4 Months Before the Show:

- Have sign-up sheets for volunteers.

- Distribute posters.

- Prepare yard signs and banners.

- Determine number of tables and chair necessary.

2 Months Before the Show:

- Deadline for entry form.

- Begin work on booklet.

- Re-check plans with venue representative.  All communications should be shared  	 	with committee members.

- Assign any other duties as they arise.

1 Month Before the Show:

- Refine the floor plan.

- Determine who will get complimentary passes.

- Complete booklet.

- Escalate publicity.

- Schedule transportation of racks and supplies from storage.

Friday Set-up:

- Plan to spend the whole day.

- Arrive at least 30 minutes before first volunteer is scheduled to arrive.

- Meet with site maintenance and review vendor set up.

- Help as needed.

Show Day:

- Arrive one hour before opening.

- Circulate, problem solve, make announcements, greet guests, etc.

- Enjoy the show.

Take Down:

- Gather and meet with all take-down volunteers to organize and fine tune the   	 	process.

Wrap-up:

- Hold meeting within one month of the show.

- Go over budget.

- Have each committee chair submit their final report and email all committee   	 	members before the meeting.

- Give final report to Guild.

- Retain $1,000 in the Quilt Show checking account

Revised 3/22/2024	Page 2 of 2 	Job Description – Quilt Show Chair